Mid-Project Progress Report

University Teaching Time Optimisation — Scenario 2: TIME  |  Group 17

Yang Feng (s2775736), Zongyuan Wang (s2794231), Yumeng Yao (s2792276), Yifei Wang (s2328864)

1. PROJECT GOAL

The project aims to quantify the feasibility and impact of two proposed reductions to the University of Edinburgh's core teaching schedule, providing the timetabling team with data-driven evidence to inform policy decisions on compressed teaching hours. Specifically, the project will:

- Scenario 1 (S1 — 9am to 5pm): Assess whether all teaching events can be accommodated within a Monday-to-Friday 9:00–17:00 window (eliminating the 17:00–18:00 slot), and determine the scale of rescheduling required.

- Scenario 2 (S2 — No Friday afternoon): Assess whether eliminating all teaching on Friday after 12:00 is feasible, and measure its impact on the rest of the week.

For each scenario the project delivers: (a) a count and breakdown of events requiring rescheduling, distinguishing whole-class lectures from subgroup sessions; (b) a clash analysis measuring how many students face overlapping timetables; (c) a lunch-break feasibility measure showing the proportion of students with a free 12:00–14:00 window; (d) room and timeslot utilisation comparisons; and (e) optimised rescheduling solutions using both an exact Mixed Integer Programming (MIP) model and a greedy/local-search heuristic.

The added value to the timetabling team is direct: rather than manual inspection of thousands of events, the project provides a fully automated analytical pipeline, reproducible on any future data snapshot, together with interpretable visualisations and concrete numeric estimates of the trade-offs between the two policy options.

2. CURRENT STATUS

Status: The project is on track and ahead of schedule.  As of 25 February 2026 (Week 3 of 9), all Phase 1 tasks (data preparation) and all Phase 2 tasks (time-constraint analysis) are complete. The heuristic optimisation model — originally planned for Weeks 5–7 — has already been built and tested, placing the team approximately two weeks ahead of the Gantt chart.

The primary technical challenge encountered was the scale of the student-event conflict graph: with 25,437 students and 31,715 events, building pairwise conflict pairs exhaustively risks O(n²) memory growth. This was mitigated by processing students in chunks and using Pandas groupby operations rather than nested loops. The clash detection routine was also redesigned to deduplicate recurring weekly slots before counting overlaps, preventing inflation of clash counts caused by the same lecture appearing as multiple Event_IDs across different teaching weeks.

The MIP optimisation component (using FICO Xpress) is currently being finalised: the model structure is complete but solver runs on the full event set are still being tuned for time-limit compliance. This is not expected to delay Milestone 2 (14 March 2026).

3. TASKS OVERVIEW

| ID | Task | Responsible | Deliverable | Status |
| --- | --- | --- | --- | --- |
| T1 | Data collection & cleaning | Yao (YY) | events.csv, student_events.csv | Done |
| T2 | Baseline utilisation analysis | Wang Z (ZW) | baseline_*.csv | Done |
| T3 | Literature review | Yao (YY) | Literature summary | Done |
| T4 | Constraint framework design | Wang Y (YW) | Constraint specification | Done |
| T5 | 9am-5pm feasibility analysis | Feng (YF) | scenario_displaced_summary.csv | Done |
| T6 | No-Friday-PM analysis | Wang Z (ZW) | S2 displaced summary | Done |
| T7 | Clash detection & analysis | Yao (YY) | clash_analysis.csv | Done |
| T8 | Lunch break feasibility | Wang Y (YW) | lunch_break_analysis.csv | Done |
| T9 | Utilisation impact comparison | Feng / Wang Z | utilisation_comparison.csv | Done |
| T10 | Data visualisation | Yao / Wang Y | 13 figures (figures/*.png) | Done |
| T11 | Sensitivity analysis | Wang Z / Wang Y | Sensitivity report | In progress |
| T12 | Heuristic optimisation | All | heuristic_*.csv | Done (ahead of plan) |
| T13 | MIP optimisation (Xpress) | All | mip_*.csv | In progress |
| T14 | Integration & final report | All | Final report | Pending (W7-W9) |

T11 (Sensitivity analysis) is the only Phase 3 task currently in progress; it will examine how results change under alternative definitions of a clash and different lunch-window durations. All other planned tasks through Week 5 are complete.

4. KEY DECISIONS AND DELIVERABLES

The following methodological decisions have been made:

- Feasibility-first optimisation: The MIP model prioritises satisfying hard constraints (every displaced event must be assigned a valid slot in the new window) before minimising soft objectives (clash count). This avoids reporting a false infeasibility when in fact a clash-free schedule is achievable.

- Lunch break as post-hoc metric: Rather than enforcing a lunch break as a hard constraint in the optimiser (which causes infeasibility for many students), lunch-window availability is computed as a descriptive metric after optimisation. This choice produces actionable statistics without artificially constraining the solver.

- Weekly-slot deduplication for clash detection: Clash counts are computed on deduplicated (module, day, start hour, semester) tuples per student, not on raw Event_IDs. This reflects real timetable conflicts (recurring weekly slots) rather than artefacts of data structure.

- Three-level clash severity: Clashes are classified as WholeClass-WholeClass (Severity 3), WholeClass-SubGroup (Severity 2), or SubGroup-SubGroup (Severity 1) to prioritise the most impactful conflicts in the objective function.

- Heuristic as MIP complement: A greedy-first, local-search-improvement heuristic was implemented to handle the full event set (up to 2,000 events), providing fast, near-optimal solutions when MIP solver time limits prevent exact optimisation.

Finished deliverables (available in code/outputs/):

- Cleaned dataset: events.csv (31,715 events), student_events.csv (25,437 students), conflict_pairs.csv

- Baseline analyses: baseline_timeslot_utilisation.csv, baseline_room_utilisation.csv

- Scenario analyses: scenario_displaced_summary.csv, clash_analysis.csv, lunch_break_analysis.csv, utilisation_comparison.csv

- Heuristic results: heuristic_assignment_S1/S2.csv, heuristic_summary_S1/S2.csv, heuristic_iteration_log_S1/S2.csv

- Visualisations: 13 figures including utilisation heatmaps, displaced-events bar charts, clash comparison charts, and heuristic convergence curves

5. PRELIMINARY RESULTS

| Metric | Baseline (S0) | S1: 9am-5pm | S2: No Fri PM |
| --- | --- | --- | --- |
| Events needing rescheduling | - | 2,024 (6.38%) | 2,693 (8.49%) |
| WholeClass events affected | - | 691 | 737 |
| Room utilisation rate | 47.21% | 49.14% | 49.47% |
| Clash pairs in timetable | 201,240 | 196,242 | 181,744 |
| Students with clashes | 56.85% | 55.08% | 53.63% |
| All-day lunch-free students | 3.64% | 4.01% | 3.99% |
| Friday lunch-free students | 38.77% | 39.38% | 70.17% |

Key finding for S1: Only 6.38% of events (2,024) fall outside the 9am–5pm window; of these, 691 are whole-class lectures spanning 686 modules. The heuristic reschedules 2,000 events and reduces the clash penalty score by 65.7% (from 39,974 to 13,697) through local search, with 94% of events placed in clash-free slots.

Key finding for S2: Removing Friday afternoon affects 8.49% of all events (2,693), virtually all concentrated on Friday itself (49.8% of Friday events displaced). The most notable benefit is a sharp rise in Friday lunch-break availability: 70.2% of students would be free on Friday 12-14:00 under S2, compared to 38.8% in the baseline.

Both scenarios slightly increase room utilisation (from 47.2% to approximately 49%), reflecting higher density of events in the reduced window. Existing timetable clashes (56.9% of students affected) are a pre-existing structural feature of the timetable, not introduced by either scenario; the optimiser can largely resolve newly-displaced events without adding new clashes.

6. CHANGES TO PROJECT PLAN

No changes to the project scope or risk register are required at this stage. The following updates reflect progress beyond the original schedule:

- Tasks T5–T10 and T12 completed in Weeks 1–3, compared to the planned Weeks 3–7. This was possible because the data cleaning step (T1) was completed efficiently in Week 1, unlocking all downstream analyses simultaneously.

- Risk R3 (infeasibility) has been partially resolved by early analysis: both scenarios are feasible in the sense that displaced events can be rescheduled within the new window, though with some residual clashes. This validates the core project premise.

- Risk R2 (computational complexity) was addressed by the chunk-based conflict-pair builder and the heuristic model, which processes 2,000 events in under two minutes on standard hardware.

The remaining schedule (Milestones M2: 14 March, M3: 28 March, M4: 10 April) remains as planned. The extra time gained will be used to strengthen the MIP solver runs and the sensitivity analysis (T11), and to produce a more comprehensive final report.